## Store Opening Checklist
RETAIL STORE OPENING CHECKLIST
Version 1.0 ¦ Goodok Shopfitting ¦ www.goodokshop.com
Instructions: Mark status as DONE when complete. Target dates are editable.
PHASE 1: PLANNING & RESEARCH (Weeks 1-4)
Status | Task | Responsible | Target Date | Done Date | Notes
TODO | Define your target market and niche | Owner | Week 1
TODO | Research competitors in your area | Owner | Week 1
TODO | Create a detailed business plan | Owner | Week 2
TODO | Determine startup budget | Owner | Week 2
TODO | Apply for business financing (if needed) | Owner | Week 2-3
TODO | Select business structure (LLC, Corp, etc.) | Owner | Week 3
TODO | Choose a business name | Owner | Week 3
TODO | Register your business | Owner | Week 4
PHASE 2: LOCATION & LEASE (Weeks 4-6)
Status | Task | Responsible | Target Date | Done Date | Notes
TODO | Identify potential locations | Owner | Week 4
TODO | Analyze foot traffic and demographics | Owner | Week 4
TODO | Negotiate lease terms | Owner/Attorney | Week 5
TODO | Review lease with attorney | Attorney | Week 5
TODO | Sign lease agreement | Owner | Week 6
TODO | Get keys and access | Owner | Week 6
PHASE 3: LICENSES & PERMITS (Weeks 5-8)
Status | Task | Responsible | Target Date | Done Date | Notes
TODO | Apply for EIN (Tax ID) | Owner | Week 5
TODO | Apply for state sales tax permit | Owner | Week 5
TODO | Apply for business license | Owner | Week 5
TODO | Health department permit (if food) | Owner | Week 6
TODO | Fire safety inspection | Fire Dept | Week 7
TODO | Obtain certificate of occupancy | City | Week 8
PHASE 4: STORE DESIGN & BUILD-OUT (Weeks 6-10)
Status | Task | Responsible | Target Date | Done Date | Notes
TODO | Create store layout plan | Owner/Designer | Week 6
TODO | Hire contractor (if needed) | Owner | Week 6
TODO | Complete electrical work | Electrician | Week 7
TODO | Install flooring | Contractor | Week 7-8
TODO | Paint walls and ceilings | Contractor | Week 8
TODO | Install lighting | Electrician | Week 8
TODO | ORDER FIXTURES AND SHELVING | Owner | Week 7
TODO | Receive and install fixtures | Owner | Week 9
TODO | Install signage | Sign Company | Week 9
PHASE 5: TECHNOLOGY & SYSTEMS (Weeks 8-10)
Status | Task | Responsible | Target Date | Done Date | Notes
TODO | Select and order POS system | Owner | Week 8
TODO | Set up internet service | ISP | Week 8
TODO | Install security cameras | Security Co. | Week 9
TODO | Set up alarm system | Security Co. | Week 9
TODO | Configure POS and train on usage | Owner | Week 10
TODO | Set up accounting software | Owner | Week 10
PHASE 6: INVENTORY & SUPPLIERS (Weeks 8-11)
Status | Task | Responsible | Target Date | Done Date | Notes
TODO | Research and contact suppliers | Owner | Week 8
TODO | Negotiate terms with vendors | Owner | Week 9
TODO | Place initial inventory orders | Owner | Week 9
TODO | Receive and inspect inventory | Owner | Week 10-11
TODO | Tag and price all items | Staff | Week 11
TODO | Organize merchandise displays | Owner | Week 11
PHASE 7: STAFFING (Weeks 8-11)
Status | Task | Responsible | Target Date | Done Date | Notes
TODO | Determine staffing needs | Owner | Week 8
TODO | Write job descriptions | Owner | Week 8
TODO | Post job listings | Owner | Week 8-9
TODO | Interview candidates | Owner | Week 9-10
TODO | Hire employees | Owner | Week 10
TODO | Set up payroll | Owner/Accountant | Week 10
TODO | Train employees | Owner | Week 11
PHASE 8: MARKETING & PROMOTION (Weeks 9-12)
Status | Task | Responsible | Target Date | Done Date | Notes
TODO | Create logo and branding | Designer | Week 9
TODO | Build website | Developer/Owner | Week 9-10
TODO | Set up social media accounts | Owner | Week 10
TODO | Create Google My Business listing | Owner | Week 10
TODO | Order business cards and marketing materials | Owner | Week 10
TODO | Plan grand opening event | Owner | Week 10
TODO | Launch social media teasers | Owner | Week 11-12
PHASE 9: FINAL PREPARATIONS (Week 12)
Status | Task | Responsible | Target Date | Done Date | Notes
TODO | Final walk-through inspection | Owner | Week 12
TODO | Test all equipment and systems | Owner | Week 12
TODO | Complete visual merchandising | Owner | Week 12
TODO | Stock checkout area | Owner | Week 12
TODO | Prepare cash drawer | Owner | Week 12
TODO | Conduct soft opening (friends/family) | Owner | Week 12
PHASE 10: GRAND OPENING (Week 13)
Status | Task | Responsible | Target Date | Done Date | Notes
TODO | Final team meeting and prep | Owner | Opening Day
TODO | Set up grand opening displays | Staff | Opening Day
TODO | GRAND OPENING! | Everyone | Week 13
TODO | Collect customer feedback | Staff | Week 13
TODO | Review first day performance | Owner | Week 13
TODO | Celebrate your success! | Everyone | Week 13
Need quality fixtures for your new store? Contact Goodok Shopfitting!
www.goodokshop.com ¦ info@goodokshop.com